## How to use
Game Development Risk Register
A free template from GameDevProducer.com. Use it to name, score, own and review the risks on your project.
How to fill it in
1. Write each risk as something that could happen, not a worry: "the netcode engineer leaves", not "staffing".
2. Score probability and impact from 1 (low) to 5 (high). Score and rating calculate automatically: 15 to 25 is High, 8 to 14 Medium, 1 to 7 Low.
3. Give every risk one named owner. A risk owned by "the team" is owned by nobody.
4. Write the early warning sign: the observable signal that the risk is starting to happen.
5. Mitigation is what you do now to make it less likely or less damaging. Contingency is the plan if it happens anyway.
6. Review the register on a fixed cadence, weekly or at every sprint review. Escalate anything rated High.
7. Delete the six EXAMPLE rows when you add your own.
Tips
Build the register with the team, not alone: the people doing the work see risks the producer cannot.
Seed it from your last postmortem. The risks that hurt your last project usually reappear in the next one under new names.
The Heat map sheet counts open risks by probability and impact so you can see where the danger is concentrated.
More: GameDevProducer.com/posts/risk-register-template-for-game-development/

## Risk register
Game Development Risk Register
Project: ____________ Producer: ____________ Review cadence: weekly or at every sprint review. Template from GameDevProducer.com. Replace the example rows with your own risks.
ID | Risk: what could happen | Category | Probability (1-5) | Impact (1-5) | Score | Rating | Owner | Early warning sign | Mitigation (before it happens) | Contingency (if it happens) | Status | Date raised | Last reviewed | Notes
R-01 | EXAMPLE: The only engineer who understands the netcode leaves or is out for weeks | Team | 3 | 5 |  |  | Lead engineer | Netcode tickets only ever assigned to one person | Pair a second engineer on netcode; document the architecture; record walkthroughs | Shortlist contractors with netcode experience; re-plan dependent milestones | Mitigating
R-02 | EXAMPLE: Console certification fails on first submission | External / platform | 3 | 4 |  |  | QA lead | Pre-cert pass finds more than a handful of requirement failures | Map every platform requirement to an owner; run an internal pre-cert pass | Hold resubmission time in the schedule before the release date | Open
R-03 | EXAMPLE: Scope grows during production without the schedule changing | Scope | 4 | 4 |  |  | Producer | Velocity flat while backlog grows sprint over sprint | Change process: new work in means existing work out, with the cost shown | Cut list agreed in advance, ranked by player impact | Monitoring
R-04 | EXAMPLE: An engine upgrade breaks the build pipeline mid-milestone | Technical | 2 | 3 |  |  | Build engineer | Upgrade branch fails nightly builds | Upgrade on a branch at the start of a milestone, never near a gate | Roll back to the previous engine version; defer the upgrade | Open
R-05 | EXAMPLE: Steam Next Fest demo not ready by the registration deadline | Schedule | 2 | 4 |  |  | Producer | Demo slice still missing core loop four weeks before the deadline | Lock demo scope early; treat the deadline as a milestone | Target the following Next Fest; reallocate the marketing plan | Open
R-06 | EXAMPLE: Live event content is late for the season start | Live ops | 3 | 4 |  |  | Live ops producer | Content not in final review two weeks before the season | Season content one beat ahead; buffer before every season start | Ship the event with a smaller content drop; move extra items to mid-season | Open

## Heat map
Risk heat map: number of open risks by probability and impact
Counts every risk on the register that is not Closed. Top-right cells are your priorities.
Probability
5
4
3
2
1
|  | 1 | 2 | 3 | 4 | 5
Impact